## Master Tracker
CS SUCCESS PLAN — MASTER TRACKER
ACCOUNT INFO | [6 empty] | STATUS |  |  | GOALS |  |  |  | MILESTONES |  |  | RISK |  | META
Account Name | CSM Owner | AE Owner | Tier | ARR / ACV ($) | Contract Start | Renewal Date | Renewal Stage | Health Score | Lifecycle Stage | Primary Goal | Goal Status | Exec Sponsor Sentiment | Champion Sentiment | Day-30 Win | Day-30 Status | Day-90 Status | Top Risk | Risk Severity | Last Updated
Acme Corp | S. Freeney | J. Patel | Tier 1 - Strategic | 85000 | 2025-01-15 | 2026-01-15 | 6-12 Months | Green | Expanding | Reduce manual reporting time by 40% | In Progress | Advocate | Advocate | First automated report delivered | Complete | In Progress | IT resource constraints on integration | Medium | 2026-04-10
BlueSky SaaS | S. Freeney | R. Chen | Tier 2 - Growth | 32000 | 2025-03-01 | 2026-03-01 | 12+ Months | Green | Adopting | Onboard 3 additional teams by Q3 | In Progress | Neutral | Advocate | Admin training completed | Complete | In Progress | Low end-user adoption in ops team | Medium | 2026-04-08
Finova Ltd | S. Freeney | M. Torres | Tier 1 - Strategic | 120000 | 2024-11-01 | 2025-11-01 | <3 Months | Yellow | Renewing | Compliance reporting automated | In Progress | Neutral | Skeptic | Compliance module configured | Complete | At Risk | Champion leaving the company | High | 2026-04-12
Greenhouse Media | S. Freeney | J. Patel | Tier 3 - Standard | 14500 | 2025-06-01 | 2026-06-01 | 12+ Months | Green | Onboarding | Content team fully adopted by month 2 | Not Started | Advocate | Neutral | Kickoff call completed | Complete | Not Started | None identified | Low | 2026-04-01
Harbor Health | S. Freeney | R. Chen | Tier 2 - Growth | 47000 | 2025-02-15 | 2026-02-15 | 6-12 Months | Red | At Risk | Reduce patient intake time by 25% | At Risk | Skeptic | Neutral | Workflow audit delivered | Complete | At Risk | Executive sponsor disengaged | High | 2026-04-14
Ironclad Logistics | S. Freeney | M. Torres | Tier 2 - Growth | 55000 | 2025-04-01 | 2026-04-01 | 3-6 Months | Yellow | Renewing | Fleet reporting consolidated to one platform | In Progress | Advocate | Advocate | Fleet dashboard live | Complete | Complete | Data sync lag in reporting module | Medium | 2026-04-09
Jasper Retail | S. Freeney | J. Patel | Tier 3 - Standard | 18000 | 2025-05-01 | 2026-05-01 | 12+ Months | Green | Adopting | Inventory alerts active across all SKUs | In Progress | Neutral | Advocate | Pilot SKU group configured | Complete | In Progress | None identified | Low | 2026-03-28
Keystone Partners | S. Freeney | R. Chen | Tier 1 - Strategic | 98000 | 2024-09-01 | 2025-09-01 | 3-6 Months | Yellow | Renewing | CSM team productivity +30% | In Progress | Advocate | Neutral | Playbook templates deployed | Complete | Complete | Budget review underway — renewal approval pending | High | 2026-04-13
Luminary EdTech | S. Freeney | M. Torres | Tier 2 - Growth | 29500 | 2025-07-01 | 2026-07-01 | 12+ Months | Green | Onboarding | LMS integration live before semester start | Not Started | Advocate | Advocate | Scoping call completed | Complete | Not Started | IT timeline may slip | Medium | 2026-04-05
Meridian Bank | S. Freeney | J. Patel | Tier 1 - Strategic | 145000 | 2024-06-01 | 2025-06-01 | <3 Months | Green | Renewing | Audit prep time reduced by 50% | Complete | Advocate | Advocate | Audit dashboard delivered | Complete | Complete | None — renewal on track | Low | 2026-04-15

## Account Summary
⬆ Select an account name from cell C3 to populate this summary
STRATEGIC SUCCESS PLAN — ACCOUNT SUMMARY
| Select Account: | Acme Corp
ACCOUNT INFORMATION
| Account Name | Acme Corp
| CSM Owner | S. Freeney
| AE Owner | J. Patel
| Account Tier | Tier 1 - Strategic
| ARR / ACV ($) | 85000
| Contract Start | 2025-01-15
| Renewal Date | 2026-01-15
CURRENT STATUS
| Renewal Stage | 6-12 Months
| Health Score | Green
| Lifecycle Stage | Expanding
SUCCESS GOALS
| Primary Goal | Reduce manual reporting time by 40%
| Goal Status | In Progress
| Exec Sponsor Sentiment | Advocate
| Champion Sentiment | Advocate
MILESTONES
| Day-30 Win | First automated report delivered
| Day-30 Status | Complete
| Day-90 Status | In Progress
RISK
| Top Risk | IT resource constraints on integration
| Risk Severity | Medium
META
| Last Updated | 2026-04-10
Integration note: In a connected stack, fields marked with * would auto-populate from Salesforce (account/contract data), Jira or ClickUp (milestone status), Gainsight or Totango (health scores), and your internal wiki (stakeholder notes). Manual entry is the fallback — but the goal is a single source of truth that updates without the CSM touching it.

## Team Dashboard
CS TEAM DASHBOARD — BOOK OF BUSINESS OVERVIEW
Formulas pull live from Master Tracker. Update the tracker — this refreshes automatically.
BOOK OF BUSINESS SNAPSHOT
| Total Accounts | Green Health | Yellow Health | Red / At Risk | High Risk Accounts | Renewing <3 Months
| 10 | 6 | 3 | 1 | 3 | 6
HEALTH BREAKDOWN BY CSM
| CSM Owner | Total Accounts | Green | Yellow | Red | High Risk | Renewing <3mo
| S. Freeney | 10 | 6 | 3 | 1 | 3 | 6
| TOTAL | 10 | 6 | 3 | 1 | 3 | 6
ACCOUNTS NEEDING ATTENTION (Red Health or High Risk or Renewal <3 Months)
| Account Name | CSM | Health | Renewal Stage | Risk Severity | Top Risk
| Finova Ltd | S. Freeney | Yellow | <3 Months | High | Champion leaving the company
| Harbor Health | S. Freeney | Red | 6-12 Months | High | Executive sponsor disengaged
| Keystone Partners | S. Freeney | Yellow | 3-6 Months | High | Budget review underway — renewal approval pending
| Meridian Bank | S. Freeney | Green | <3 Months | Low | None — renewal on track
Integration note: In a fully connected stack, this dashboard pulls live from Salesforce (accounts, ACV, renewal dates), Gainsight/Totango (health scores), Jira (milestone status), and your support platform (open ticket count). Manual entry in the Master Tracker is the interim approach — the architecture is the same either way.